## Table 1
CIP Project # | Priority Year | Projects | Category | Work Description | Linear Feet | From | To | Material Cost (Improvements) | Other Costs (Replacement) | TOTAL COST
M1 | 2022 | Convert Spings water tank to dry storage | Improvement | Repurpose water tank |  | Dockton Springs |  | 3000 |  | 3000
M2 | 2022 | Demo Old Well House | Replacement | Demo Building |  | 268th/Hake Property |  | 12000 |  | 12000
M3 | 2022 | DWA Buidling Improvements | Replacement | Improvements to ex. Building |  | Main building soffits and facade, replace roof and gutters in storage room |  | 25000 |  | 25000
Proposed Cost for 2022/2023 | [9 empty] | 40000
D1 & M4 | 2024 | Lower Shores Main Improvements and Sandy Shores PRV Replacement | Replacement | 8" Replacememt | 1850 | SW 275th St | Shores Dr SW Ter | 565800 | 174500 | 740300
D2 | 2025 | 94th to Pt. Piner Connection | Improvement | 8" Extension | 1110 | 94th Ave SW | Pt. Pinner | 331400 | 102200 | 433600
|  |  |  | Proposed Cost for 2024/2025 | [5 empty] | 1173900
D3 | 2026 | Hake Road Pipe Replacement | Improvement | 8" Replacement | 3500 | SW 268th St Terminus | Hake Road Terminus | 951400 | 293300 | 1244700
Proposed Cost for 2026 | [9 empty] | 1244700
D4 | 2027 | 275th | Replacement | 8" Replacememt | 1945 | 94th Ave SW | Sandy Shores Dr SW | 557000 | 171700 | 728700
Proposed Cost for 2028 | [9 empty] | 728700
D5 | 2029 | 94th | Replacement | 8" Replacememt | 1620 | Sandy Shore Well | 94th- Summerhurst Connection | 491000 | 151400 | 642400
Proposed Cost for 2031 | [9 empty] | 642400
D6 | 2032 | 274th and 90th | Replacement | 8" Replacememt | 2300 | 94th Ave SW | 90th Ave SW | 660300 | 203600 | 863900
Proposed Cost for 2034 | [9 empty] | 863900
CIP Project# | Priority Year | Projects | Category | Work Description | Linear Feet | From | To | Material Cost (Improvements) | Other Costs (Replacement) | TOTAL COST
D7 | 2037 | 99th | Replacement | 8" Replacement | 3100 | SW Windmill | SE 268th St | 849500 | 261900 | 1111400
D8 | 2038 | 265th | Replacement | 8" Replacememt | 730 | 99th Ave SW | 265th Terminus | 225700 | 69600 | 295300
D9 | 2039 | 263rd | Replacement | 8" Replacememt | 1330 | 99th Ave SW | 263rd Terminus | 377000 | 116200 | 493200
D10 | 2041 | 262nd | Replacement | 8" Replacememt | 900 | 99th Ave SW | 262nd Terminus | 264000 | 81400 | 345400
D11 | 2042 | Summerhurst Loop | Improvement | 8" Extension | 950 | 94th to Summerhurst Connection | Summerhurst to Sandy Shores Connection | 275100 | 84800 | 359900
D12 | 2043 | Summerhurst to Sandy Shores Connection | Improvement | 8" Extension | 1000 | Sandy Shores | Summerhurst | 298000 | 91900 | 389900
D13 | 2045 | Summerhurst Walk | Improvement | 8" Extension | 2200 | Summerhust | Pt. Piner | 624100 | 192400 | 816500
D14 | 2046 | Point Pinner to 288th Connection | Improvement | 8" Extension | 2210 | Pt Piner | SW 288th St | 626400 | 193100 | 819500
D15 |  | Hake Rd. and Manzanita Connection | Improvement | 8" Extension | 300 | Hake Rd. Terminus | Manzanita Terminus | 112500 | 34700 | 147200
ST1 |  | 1600,000 Gal Storage Tank | Improvement | Storage |  | Storage Tank Site |  | 685400 | 90600 | 776000
S1 |  | Shandy Shores Well Pump Replacement | Improvement | Source |  | Sandy Shores Well |  |  | 10800 | 10800